## Sheet1
| Table using current Allocations Plan and sites with permission only |  |  | balance |  | completions (sites over 5 net) | [5 empty] | actual |  | Minimum deliverable | [5 empty] | Minimum available 2029-34 (developable) | [6 empty] | 2024 draft ref if any
| Address and planning ref no/ HLA reference | sums | capacity | 2024-03-01 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | complete | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 5 yr NPPF | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 5yr NPPF | comments | 2024 LP
| Alvington Clanna Lane 1494/15. 1772/18 RM. 2990 11 | 11 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | RM approved April 2019 commenced Dec 2021 10 complete summer 2023
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Bream Ryelands Rd (Woodside) 0546/13, P0422/18/FUL. 2002 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | allocated site has tech commencement full permission for 9 DISCON 13/21- part of an allocation for 15 | LP83
| Bream New Rd/ High St (RFC) site 1082/14. 1217/19 full 0546/22 revision 2973 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | AP full pp for 8 (Oct 2020, exp Oct 2023) | LP84
| Bream New rd/ High Street 0636/15, 1736/17. 2871 | 9 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | allocated in AP 9 dwellings now complete
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Cinderford Football Club Causeway Rd. 80 | 50 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | Allocated site no permissions or application- has been subject to pre application discussion | LP46
| Cinderford NQ AAP Newtown Rd site 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | sold for another use, not counted in housing land supply inside dsb but not allocated in draft LP
| Cinderford Northern Quarter, AAP 0663/14 2843 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | outline pp hybrid which has been part implemented site (FoDDC owned) under review | LP45
| Cinderford Railway Tavern Station St 0509/16/ful 0469/22. 2367 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | revision approved additional 2 units approved 2023 u/c
| Cinderford St Whites Farm Sneyd Wood Rd 0558/11 2070 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20 | 0 | 0 | 0 | 50 | developable- part covered by unimplemented (valid) consent at pre application stage now allocated in draft LP | LP48
| Cinderford St Whites Rd Peacock Lane Ruspidge 0678/13. | 16 | 16 | 0 | 4 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Cinderford Station St former Listers (Rothdean) and ex foundry 1590/04 1292 130 | 130 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 34 | 33 | 30 | 0 | 130 | site available- within plan allocation pre app stage former Listers factory and Cannop Foundry | LP47
| Cinderford Station St Turley Ct and Wilce land 0885/10 2453 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | site available- within plan allocation no recent application adjoins larger site in different ownership | LP47
| Cinderford Valley Road former Engelhards 1175/18 0577/20 49 | 49 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 24 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | O/L pp 29 09 2022 (49 units and employment space) revised site for draft LP but outline pp for previous scheme | LP49
| Cinderford former St Anthony's school 0971/21 pp subsequent discons 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | conversion to 8 units permitted and completed
| Cinderford St Whites former school consent 1480/19 3139, conversion site 8 | 9 | 8 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all completed April 2023
| Cinderford St Whites former school 0827/20 3399, 2073/21 new build site 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 new build units permitted approval materials etc 2022. Site works underway
| Cinderford Sneyd Wood Rd North 1883/21ful 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | AP allocation full application approved with S 106 agreement Nov 2023 not allocated in draft LP
| Cinderford 17 Foundry Road | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Cinderford former health centre 1228/20PIP 3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Permission in Principle for 8 units expired 16/09/2023 future unknown
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Coleford former Dukes Travel Lakers Rd Berry Hill 1002/17 1814 | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Coleford former Kings Head application 1266/18. 3256 3 | 8 | 8 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 completed 2019, 4 under construction 09 2022. complete 04/24
| Coleford Lawnstone Hse High St 0067/18 3102 | 10 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all completed 2019
| Coleford Newland St former WCs 0285/16. 2644 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no change for many years some foundation work completed
| Coleford Owen Farm Staunton Rd 1167/13 | 90 | 90 | 0 | 42 | 38 | 10 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | final phase completed by June 2018
| Coleford Poolway Farm Gloucester Rd 1105/22 90 1594/23 140 | 140 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 0 | 140 | allocated site at full application 1594/23 for 140dwellings by housebuilder | LP52
| Coleford Milkwall Ellwood Rd 2100/21/ful 48. | 47 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 24 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | resolved to permit scheme for 47 (April 2024) previously allocated | LP54
| Coleford Kings Meade addition 48 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | allocated site remains at early pre application stage | LP55
| Coleford North Road Worcester Walk Broadwell 3527 0635/19 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 35 | 20 | 15 | 0 | 0 | 0 | 35 | allocated site part with permission in outline (09/23) | LP56
| Coleford Ex Sonoco Tufthorn Avenue P0912/16/OUT, 2002/18RM. 1282/23 3161 | 64 | 65 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 16 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | total complete 64. appeal dismissed re revised scheme on remainder of site
| Coleford Ross Rd Christchurch Hall P1263/13 2951 up to 4 2022 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Coleford Milkwall Club 0227/18 3179 | 4 | 9 | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | site uc part complete remainder in small site figures
| Coleford Lower Lane Berry Hill 1482/14 (appeal) and 1547/19. 3260 203 | 203 | 203 | 28 | 0 | 0 | 0 | 0 | 0 | 47 | 60 | 68 | 175 | 28 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | capacity now 203, 60 completed 2022/23 68 in 2023/24
| Coleford Marians Walk Berry Hill 1583/20 pp 17 3470 | 17 | 17 | 17 | actual 2023/24: 0 | 0 | 17 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | permission Jan 2023 exceptions site now commenced added to dsb indraft LP but not allocated
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Drybrook Farm Drybrook Rd 1753/12 2640 18 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 17 | AP allocation has had outline PP part of revised LP allocation | LP86
| Drybrook High Street 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 0 | 0 | 0 | 50 | allocation in AP revised scheme at pre app stage part of revised LP allocation | LP86
| Drybrook High St adj RFC1729/16. 0457/20 RM 3147 | 57 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 24 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed 2022/23
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Hartpury adj Village Hall Over Old Rd. 2015/20 full appn 3385 variation 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | AP allocation- full application now permitted (Nov 2021), commenced summer 2023
| Hartpury Over Old Road resolved to grant permission 0293/22 (26) | 26 | 26 | 26 | actual 2023/24: 0 | 0 | 0 | 0 | 15 | 11 |  | 26 | [5 empty] | 0 | current application awaiting notice allocated as permission in new LP | LP87
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Huntley The Poplars Tibberton Lane 0946/20 outline RM197/23 10 3339 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | AP allocation outline consent Apr 2021 RM application aproved June 2023 commenced not allocated in draft
| Huntley Broom Hill Woodend Farm 1642/17 3248 conversion 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | Conversion of farm buildings some conditions discharged
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Littledean Beech Way 0899/14 0992/16 app. 2068/20var 2884 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 10 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | allocation with permission appn to vary conditions approved Oct 2022 technical start allocated in draft LP | LP91
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Longhope Church Road 1975/11, 0471/17 Sept 2019 1637/19discon. 2611 2uc 23 | 23 | 23 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 7 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | revised full permission for 23 now under construction/ complete
| Longhope Church Road 1266/21 3551 12 (CLT scheme) | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | exceptions scheme commencement early 2024
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Lydbrook former Rothdean tinplate wks 1303/13 1165/17 RM 1010 26 | 26 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | AP allocation and RM now approved | LP92
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Lydney East "Liddington" land adj Naas lane & bypass. 1186/22/ful 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 30 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | linked to adjoining site on this site 70 10/ 23 on site | LP63
| Lydney East (east of Oakdale) 1881/15 1399/18. 2391 347 | 347 | 347 | 145 | 0 | 0 | 0 | 30 | 50 | 25 | 62 | 35 | 202 | 40 | 40 | 40 | 25 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | permission for 347 dwellings about 200 currently complete, uc post 2022/23 del 180 | LP63
| Lydney East Phase A (RHL site) 0412/13, 0745/18 2417 320 876.23 app for 200 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 135 | 45 | 20 | 0 | 0 | 0 | 65 | part of allocated site (Lydney A) this part has detailed consent or 200 with developer on site (Bellway) | LP63
| Lydney East Phase A remainder 0745/18 o/l 80 units? | 80 |  | 0 | [11 empty] | 0 |  |  |  |  | 0 | 40 | 40 | 0 | 80 | remainder of Lydney A Harris land and small area N of Naas Lane. Has outline consent. | LP63
| Lydney East Phase B (RHL site) 0361/15 Redrow 0076/17. 2471.1 | 125 | 125 | 0 | 0 | 21 | 38 | 46 | 20 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed (125) 2020/21
| Lydney east Phase B (Bellway) 0835/17. 2471.2 | 90 | 90 | 0 | 0 | 5 | 49 | 24 | 12 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed (90) 2020/21
| Lydney east Phase B remainder. 2471 R3 160 | 160 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 40 | 20 | 0 | 160 | remainder of Lydney B with outline consent capacity 150 or 160 approx at pre application stage | LP63
| Lydney Highfield Rd rear T & T 1829/13, 0108/17 0370/19. 2806 | 177 | 177 | 0 | 0 | 0 | 20 | 43 | 56 | 43 | 6 | 9 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | almost all complete by March 2024 total 177. | LP63
| Lydney Holms Farm , 1889/15 29 3211 as revised allocation RMsubmitted 702/24 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | allocation 2005 LP and AP, permission for one conversion and outline for remainder (29) rm submitted
| Lydney Augustus Way Allaston 1284/13, 1591/18APP 3057 200 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 30 | 48 | 30 | 30 | 30 | 30 | 32 | 152 | o/l for 200 phase 1 RM appn approved (18) commencement before Oct 2022 (earthworks) | LP65
| Lydney 33 High Street 1095/18. 3130 uc 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Lydney B part 2471.3 2471.3 0258/20 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 8 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete part of Lydney B | LP63
| Lydney B part 2471.4 Crest 148 | 148 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 70 | 38 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete part of Lydney B | LP63
| Lydney B part 0260/20 D Wilson 64 | 67 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 28 | 6 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete part of Lydney B | LP63
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Mitcheldean Former coach depot St Michaels Close 12 1617/23 11 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | AP allocation current application 1617/23 for 9 | LP94
| Mitcheldean former George Hotel 1849/14 1106/18 RM pp. 2878 expired 2A72:V72/21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | AP allocation previous outline permission | LP94
| Mitcheldean Glos Rd 0086/09 | 7 | 51 | 44 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete
| Mitcheldean Bradley Court Rd (Vantage Point) 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | proposed AP allocation not counted in five year supply- no progress
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Newent Ross Rd mixed development site. 0855/19 o/l 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | mixed allocation in AP previous refusal for part development
| Newent Ross Rd (Bellway) Horsefair Lane RM approved 0328/18. 2885 | 85 | 85 | 0 | 0 | 0 | 5 | 41 | 39 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | completed 2020/21
| Newent ex Nursery Southend Lane 1877/13, 0047/16. 0981/19 s106 2834 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Newent Watery Lane 1513/13, 1915/15 revised scheme 1338/20 2777 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | new full approval April 2021 1338/20 all under construction
| Newent Southend Lane North 1330/18. 0041/20RM approved 3218 80uc 230. | 230 | 230 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 104 | 94 | 222 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | allocated in AP, nearing completion 8 remaining to be completed March 2024.
| Newent Southerns Barn Southend Lane 241/20 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Newent Cleeve Mill Lane Gloucester Rd 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 20 | 0 | 0 | 0 | 45 | AP allocated site no application | LP75
| Newent Court Road 1854/13 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | small redevelopment completed
| Newent Glebe Gospel Chapel 1746/17 0039/19. 3105 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Newent Bradfords Lane 1990/18 ol RM 1086/21 3400 uc 50 | 50 | 50 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 39 | 49 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | first completions 2021/22 one remaining to be completed March 2024
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0
| Newnham former Victoria Hotel High St 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | AP allocation some remedial work completed no application | LP97
| Newnham north of Newnham off A 48 1733/18FUL uc 3290 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 35 | 42 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | AP allocation- site complete 2023/24, application for additional adj phase allocated in draft
|  | 0 |  | 0 | [8 empty] | 0 | [9 empty] | 0 | 0 | 0
| Redmarley Drury Lane 1593/14 0058/17. 2963 | 8 | 8 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Redmarley Adj RockMeadow (east of) 0917/21 3412 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | under construction April 23
| Redmarley Paget nursery 181/19 ful 3076 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0
| Sedbury Former church Grahamstown Rd 3333 1969/20 pp 30 04 2021 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | full consent April 2021 but acquired for office use permitted in 2023, 1288/23
| Sedbury Tutshill A48 adj Bigstone Gloucester Rd 1911/15 651/17. 2946 | 45 | 45 | 0 | 0 | 0 | 13 | 18 | 14 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete
| Sedbury Tutshill Gloucester Rd RM approved 1937/17. 2912 | 91 | 91 | 0 | 0 | 0 | 12 | 34 | 35 | 10 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete
| Sedbury/ Tutshill Adj Wyedean School 1792/13, 1557/15. 2819 110 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 27 | 57 | 26 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete 2022/23
| Sedbury/ Tutshill former garage adj Ormerod Rd 0815/17. 3136 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | site complete
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0
| Sling Adj Miners Arms 0706/05 2035 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | preapp stage 12/20 no further information | LP99
| Sling former builders yard 0452/21 9 3380 | 9 | 9 | 9 | [8 empty] | 0 |  | 0 | 0 |  |  | 0 | 9 |  |  | 0 | 0 | 9 | permitted (o/l) 10/1previous outline consent still valid and now revised full application
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0
| Staunton Corse Gloucester Rd o/l 1232/18. 1229/19 (RM) 3194 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | all complete
| Staunton Corse Chartist Way RM appn 848/18. 3044 remainder comp? 5 | 27 | 27 | 0 | 0 | 0 | 0 | 1 | 21 | 5 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | complete
| Staunton Corse former garden Centre 0731/22 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 16 |  |  |  | 0 | 0 | 0 | full application permitted October 6 2022 DISCON approved not started
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0
| Whitecroft Scovill Lydney Rd Whitecroft. 0919/19 resolved to grant o/l for 66 | 66 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 0 | 0 | 66 | outline application delegated approval June 23 awaiting S106 | LP101
|  | 0 |  | 0 | [8 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0
| Woolaston/ Netherend Ash Way 1715/22 OUT application 12 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | allocated site for about 12, current outline appn for 11 | LP102
| Woolaston/ Netherend Farm 1995/18 out 1768/22 RM pending 2230 36 | 36 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | outline permission June 2021 RM approved 25 07 23
|  | 3071 |  |  | completions (sites over 5 net) 2019/20: 254 | 2173 | 155 | 138 | 192 | 249 | 164 | 898 | [5 empty] | 0
[19 empty] | 0 | [5 empty] | 0
| total in column above |  | 4211 | 2026 | 53 | 77 | 170 | 508 | 298 | 451 | 488 | 382 |  | 155 | 138 | 192 | 249 | 164 | 898 | 362 | 374 | 195 | 155 | 32 | 1118
| total all large sites if different to above |  |  |  | 165 | 187 | 192 | 263 | 298 | 451 | 488 | 307 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| Small sites estimate/ counted |  | 1768 |  | 82 | 69 | 78 | 73 | 60 | 41 | 29 | 49 |  | 40 | 40 | 40 | 40 | 40 | 200 | 40 | 40 | 40 | 40 | 40 | 160
| large windfall estimate if applicable | [13 empty] | 0 | 0 | 16 | 32 | 48 | 40 | 40 | 40 | 40 | 40 | 200
| total annual net completions or potential |  |  |  | 247 | 256 | 270 | 336 | 358 | 492 | 517 | 431 | 2907 | 195 | 178 | 232 | 305 | 236 | 1146 | 442 | 454 | 275 | 235 | 112 | 1406
| completions on large sites not named above included in annual total |  |  |  | 112 | 110 | 22 |  | 0 | 0 |  |  | 1440
from NPPF supply only, calculation for trajectory from this spreadsheet
NPPF compliant
| Annual requirement |  | 330
| five year net requirement |  | 1645
| backlog (difference between annual requirement *17 and completions) |  | na
| sub total |  | 1645
| sub total plus 5%= five year requirement |  | 1727.25
| minimum dwellings available |  | 1146
| years' supply for plan |  | 3.3174
maximum available
years' supply for plan
SUMMARY OF COMPLETIONS ON SITES OVER FIVE DWELLINGS (NET)
| SITE ADDRESS with planning reference | grid ref approx | capacity | complete | 2023/24 | 2022/23 | 2021/22 | 2020/21 | 2019/20 | 2018/19 | 2017/18 | 2016/17 | 2015/16 | 2014/15 | 2013/14 | 2012/13
Alvington | Clanna Road 1772/18 | 360261201009 | 11 | 10 | 2016/17: 10
Blakeney | former Goods Station | 367002206813 | 17 | 17 | [8 empty] | 17
Bream | New Rd 1736/17 | 360143205797 | 9 | 9 | completions (sites over 5 net) 2021/22: 9
Bream | Parkend Rd no 23 net 9 total 13 | 360706206660 | 9 | 9 | actual 2023/24: 9
Churcham | Birdwood adj former Chapel | 374171218689 | 7 | 7 | actual 2023/24: 7
Churcham | Bulley Farm barns | 376193219678 | 6 | 1 | bar: 2016/17 to actual 2023/24
Cinderford | Commercial St no 3 net 7 | 365607213878 | 7 | 7 | [8 empty] | 7
Cinderford | Foundry Road no 17 | 365523214043 | 8 | 8 | completions (sites over 5 net) 2022/23: 8
Cinderford | Hanover Court valley Rd | 365139214088 | 20 | 20 | [8 empty] | 20
Cinderford | Hollydean net capacity 5 gross 15 | 365406214432 | 5 | 5 | [10 empty] | 5
Cinderford | Market St 32 7 | 365650213983 | 7 | 7 | [9 empty] | 7
Cinderford | Royal Foresters Court ex PH | 366430214306 | 7 | 7 | [8 empty] | 7
Cinderford | Ruspidge Bracken Close 7 | 365524212637 | 7 | 0
Cinderford | Ruspidge Villa 6 | 365530212583 | 6 | 6 | [8 empty] | 6
Cinderford | St Anthony's School | 365951213640 | 8 | 8 | 2016/17: 8
Cinderford | St Johns Parish Hall 0344/14 St Johns Mews | 365240212684 | 11 | 11 | actual 2023/24: 5 | 3 | 3
Cinderford | St Whites Bloor HLA2070 Sneyd Wood Road | 365647212830 | 174 | 60 | [9 empty] | 13 | 27 | 20
Cinderford | St Whites Rd Peacock Lane Ruspidge 0678/13 etc | 365277212500 | 18 | 18 | completions (sites over 5 net) 2021/22: 7; completions (sites over 5 net) 2022/23: 0; actual 2023/24: 4 | 2 | 5
Cinderford | St Whites former school St Whites Rd | 365484212847 | 8 | 8 | completions (sites over 5 net) 2017/18: 7; completions (sites over 5 net) 2018/19: 1
Cinderford | Valley Road 1238/12 Cinders Crescent | 365056213618 | 92 | 92 | [8 empty] | 25 | 51 | 16
Coleford | Angel Farm Persimmon HLA2231 Lawdley Rd etc | 357842210241 | 100 | 64 | [10 empty] | 21 | 43
Coleford | Bank Street 0438/13 Dora Matthews Hse | 358151210721 | 49 | 49 | [9 empty] | 49
Coleford | Berry Hill Lower Lane Ridgeway Avenue | 358729211773 | 180 | 175 | 2016/17: 68; completions (sites over 5 net) 2017/18: 60; completions (sites over 5 net) 2018/19: 47
Coleford | Christchurch 1263/13 Former School | 357145213013 | 6 | 6 | completions (sites over 5 net) 2018/19: 4; completions (sites over 5 net) 2019/20: 2
Coleford | Coalway Rd 27-41 1160/11 Poppy Field | 358470210567 | 41 | 41 | [8 empty] | 39 | 2
Coleford | Foxes Lane Broadwell DF6441, 0055/10 | 358884210892 | 7 | 7 | [9 empty] | 7
Coleford | High Nash 0832/06 Byrons Meadow | 357734209985 | 7 | 0
Coleford | High Nash House High Nash | 357693210114 | 7 | 7 | actual 2023/24: 7
Coleford | Kings Head 1266/18/ful | 357857210441 | 8 | 8 | 2016/17: 4; completions (sites over 5 net) 2020/21: 4
Coleford | Kings Meade 1727/07 | 357853210455 | 14 | 14 | actual 2023/24: 14
Coleford | Lakers Rd 1967/17 Dukes Close | 358185212498 | 7 | 7 | completions (sites over 5 net) 2021/22: 7
Coleford | High Street Coleford 0067/18 Foxglove Gdns | 357630210541 | 10 | 10 | completions (sites over 5 net) 2020/21: 10
Coleford | Milkwall Club 0227/18 HLA 3179 | 358397209144 | 7 | 2 | completions (sites over 5 net) 2018/19: 2
Coleford | Milkwall Station Road Forest Road | 358418209227 | 6 | 0
Coleford | Old Brewery DF10473 | 357610210831 | 6 | 0
Coleford | Owen Farm 1167/13 | 357060211113 | 156 | 156 | completions (sites over 5 net) 2021/22: 10; completions (sites over 5 net) 2022/23: 38; actual 2023/24: 42 | 56 | 10
Coleford | Pike House B Hill | 357260211966 | 12 | 0
Coleford | Sunnybank Copper Beech Close | 358851210891 | 6 | 6 | [8 empty] | 6
Coleford | Tufthorn Ave ex Sonoco 0912/16, 2002/18 HLA 3161 | 358934209417 | 65 | 64 | completions (sites over 5 net) 2017/18: 17; completions (sites over 5 net) 2018/19: 47
Coleford | Tufthorn hla2580 net increase C11 | 358917209066 | 9 | 9 | [10 empty] | 5 | 4
Coleford | Woodgate Rd 25 | 359173211836 | 26 | 9 | [9 empty] | 6 | 1 | 2
Drybrook | High St DF10391/D | 365111217407 | 26 | 0
Drybrook | High St Mannings Farm 0457/20, 1729/16 | 365092217671 | 57 | 57 | completions (sites over 5 net) 2017/18: 24; completions (sites over 5 net) 2018/19: 33
Drybrook | Nelson Arms | 364150217245 | 6 | 6 | actual 2023/24: 6
Dymock | Western Way Winding Pool Close | 370542230868 | 20 | 20 | [8 empty] | 20
Hartpury | Over Old Rd School Close | 380219224740 | 13 | 13 | [11 empty] | 13
Huntley | Orchard Way DF3960 The Fairways | 372779219308 | 33 | 0
Littledean | off Oak Way Littledean Three Trees Way | 367187213681 | 9 | 0
Longhope | Church road 1637/19 discon | 368408219640 | 23 | 8 | 2016/17: 8
Lydbrook | Orchard Road Joys Green | 360477216406 | 7 | 7 | [11 empty] | 7
Lydney | adj Health Centre Taurus House | 363694203406 | 8 | 0
Lydney | East Bellway 0835/17 Barnett Way | 364862213715 | 90 | 90 | completions (sites over 5 net) 2019/20: 12; completions (sites over 5 net) 2020/21: 24; completions (sites over 5 net) 2021/22: 49; completions (sites over 5 net) 2022/23: 5
Lydney | Lydney B part 2471.3 2471.3 0258/20 40 | 364439203816 | 40 | 40 | 2016/17: 8; completions (sites over 5 net) 2017/18: 32
Lydney | Herbert Howells Way Wintour Drive Redrow | 364363203593 | 125 | 125 | completions (sites over 5 net) 2019/20: 20; completions (sites over 5 net) 2020/21: 46; completions (sites over 5 net) 2021/22: 38; completions (sites over 5 net) 2022/23: 21
Lydney | East Crest 1953/19 etc | 364581203551 | 148 | 148 | 2016/17: 38; completions (sites over 5 net) 2017/18: 70; completions (sites over 5 net) 2018/19: 40
Lydney | East Barratt D Wilson 0260/20 Glastonbury Dr | 364273203690 | 67 | 67 | 2016/17: 6; completions (sites over 5 net) 2017/18: 28; completions (sites over 5 net) 2018/19: 33
Lydney | High Street( rear of no33) 1095/18 | 363008203007 | 9 | 9 | 2016/17: 9
Lydney | Highfield Hill Edenstone 1829/13 Abbots Gate | 365138203684 | 177 | 177 | 9 | 6 | 43 | 56 | 43 | 20
Lydney | Highfield Rd 1089/11 (HLA2069) Meadow Rise | 364912203199 | 47 | 47 | [8 empty] | 18 | 16 | 13
Lydney | Naas Lane net 7 redevelopment Meadow View | 364444203118 | 7 | 0
Lydney | Oakdale 1009/09 Overstreet Green | 364684202356 | 200 | 167 | [9 empty] | 30 | 98 | 39
Lydney | 5, 7 Orchard Rd 1691/14 | 364190202687 | 4 | 4 | actual 2023/24: 4
Lydney | Persimmon Kingfisher Dr 1399/18, 1885/15 etc | 364600202503 | 347 | 202 | 35 | 62 | 25 | 50 | 30
Lydney | Pylers way 0762/12 net 7 | 363887202698 | 7 | 7 | [9 empty] | 7
Lydney | Regent Street ex Job Centre | 363610203143 | 10 | 10 | [11 empty] | 10
Lydney | Severnleigh Naas Lane | 364240203108 | 8 | 9 | completions (sites over 5 net) 2022/23: 9
Lydney | Tutnalls Klondike Ave DF13997 gross19 | 363884203077 | 13 | 0
Mitcheldean | Eastern avenue 1389/09 | 366810218511 | 7 | 0
Mitcheldean | Gloucester Rd Dean Meadows | 366810218491 | 51 | 51 | actual 2023/24: 8 | 9 | 17 | 17
Newent | Cleeve Mill E Care 1034/11 Mill Park | 372886226136 | 17 | 17 | completions (sites over 5 net) 2022/23: 17
Newent | Bradfords Lane 1086/21 RM | 371445225923 | 50 | 49 | 2016/17: 39; completions (sites over 5 net) 2017/18: 10
Newent | Court Lane 1854/13 | 372257225909 | 6 | 6 | completions (sites over 5 net) 2017/18: 5; completions (sites over 5 net) 2019/20: 1
Newent | Culver St (Craddocks) net 5 | 372108225459 | 5 | 5 | [10 empty] | 2 | 3
Newent | Culver St Redford Place 31 | 372231225696 | 6 | 6 | actual 2023/24: 6
Newent | Culver St Whitegates 1597/09 | 372318225292 | 13 | 13 | [11 empty] | 13
Newent | Foley Rd (Linden Homes) 0264/10 Drovers Way | 372461225442 | 98 | 98 | [9 empty] | 27 | 50 | 21
Newent | Foley Road 0974/15 Manor Road | 372410225256 | 120 | 120 | completions (sites over 5 net) 2022/23: 68; actual 2023/24: 52
Newent | Glebe Rd (former chapel) Glebe Court | 372185226048 | 9 | 8 | completions (sites over 5 net) 2018/19: 8
Newent | Meek Rd DF13239/A 141 total D Wilson | 372925225376 | 141 | 4 | [11 empty] | 4
Newent | Ross Rd Bellway 0328/18 Valegro Avenue | 371746226129 | 85 | 85 | completions (sites over 5 net) 2019/20: 39; completions (sites over 5 net) 2020/21: 41; completions (sites over 5 net) 2021/22: 5
Newent | Southend Lane North 1330/18, 0041/20 | 372598225059 | 230 | 222 | 2016/17: 94; completions (sites over 5 net) 2017/18: 104; completions (sites over 5 net) 2018/19: 24
Newent | Southend Lane Poinsettia Way 0981/19, | 372565224887 | 36 | 36 | completions (sites over 5 net) 2018/19: 36
Newent | Southend Lane Southerns Barn 0241/20 | 372344224912 | 6 | 6 | completions (sites over 5 net) 2018/19: 6
Newnham | North of Village off A48 1733/18 | 369857211575 | 80 | 80 | 2016/17: 42; completions (sites over 5 net) 2017/18: 35; completions (sites over 5 net) 2018/19: 3
Newnham | Sheens Meadow DF13276 | 369488211732 | 27 | 2 | [10 empty] | 1 | 1
Redmarley | Drury Lane 1593/14 Covent Garden | 375736232331 | 11 | 8 | 2016/17: 4; completions (sites over 5 net) 2017/18: 0; completions (sites over 5 net) 2019/20: 1; completions (sites over 5 net) 2020/21: 3
Redmarley | Hyde Pk Corner 1550/12 | 375743231335 | 10 | 10 | [9 empty] | 10
Redmarley | Rock Meadow | 375406231386 | 10 | 10 | [9 empty] | 10
Redmarley | Paget Nursery The Vines | 375253231064 | 9 | 9 | completions (sites over 5 net) 2017/18: 1; completions (sites over 5 net) 2019/20: 8
Sling | Miners Close Sling redevelopment net increase 4 | 358257207924 | 4 | 4 | [11 empty] | 4
Soudley | former Coach depot, Bevan Rise | 366327210498 | 13 | 0
St Briavels | Smithville Close | 356792204435 | 9 | 9 | completions (sites over 5 net) 2022/23: 9
Staunton Corse | Chartist Way 1680/11 Freedom Close | 378740229094 | 15 | 15 | [10 empty] | 15
Staunton Corse | Chartist Way 27 Hetherington Close | 378703229124 | 27 | 27 | completions (sites over 5 net) 2018/19: 5; completions (sites over 5 net) 2019/20: 21; completions (sites over 5 net) 2020/21: 1
Staunton Corse | Corse Grange 0114/13 | 379300228687 | 7 | 7 | completions (sites over 5 net) 2022/23: 7
Staunton Corse | Gloucester rd Yew Tree Close | 379579228757 | 27 | 27 | completions (sites over 5 net) 2018/19: 27
Tibberton | Old Forge 0287/13 Bramble Close | 376688221696 | 9 | 9 | [8 empty] | 9
Tutshill Sedbury | adj Ormerod Rd The Beeches | 354644193620 | 10 | 10 | completions (sites over 5 net) 2019/20: 10
Tutshill Sedbury | adj Wyedean School Crane Pool Ave 1792/13 | 354989194028 | 110 | 110 | completions (sites over 5 net) 2017/18: 26; completions (sites over 5 net) 2018/19: 57; completions (sites over 5 net) 2019/20: 27
Tutshill Sedbury | Bigstone Meadow DF8773 | 354341194587 | 44 | 0
Tutshill Sedbury | Cross Keys Court | 354438194608 | 12 | 0
Tutshill Sedbury | Birch Grove adj Bigstone 1911/15, 0651/17 | 354670194716 | 45 | 45 | completions (sites over 5 net) 2019/20: 14; completions (sites over 5 net) 2020/21: 18; completions (sites over 5 net) 2021/22: 13
Tutshill Sedbury | Gloucester Rd Ash Cres. Bellway 1937/17, 1530/14 | 357649194556 | 91 | 91 | completions (sites over 5 net) 2018/19: 10; completions (sites over 5 net) 2019/20: 35; completions (sites over 5 net) 2020/21: 34; completions (sites over 5 net) 2021/22: 12
Tutshill Sedbury | Park View Works Sedbury Court DF4961/J | 354740193459 | 14 | 0
Whitecroft | Lydney Rd Redrow 0010/13 Kidnalls Drive | 362377206052 | 49 | 49 | [9 empty] | 40 | 9
Woolaston | Severn View rd Bridge View | 359820200081 | 6 | 0
Yorkley | former bakery 0593/05 The Rudge | 363383206843 | 14 | 0
| Total on above listed sites |  | 4189 | 3405 | 382 | 487 | 451 | 296 | 254 | 170 | 182 | 165 | 244 | 310 | 280 | 184
some sites with completions pre2012/13 listed above for informtion | small sites |  |  |  | 49 | 30 | 40 | 62 | 73 | 99 | 74 | 82 | 69 | 86 | 75 | 82
[5 empty] | 382 | 487 | 453 | 295 | 261 | 170 | 182 | 165 | 244 | 310 | 280 | 184
| completions recorded above |  |  |  | 431 | 517 | 493 | 357 | 334 | 269 | 256 | 247 | 313 | 396 | 355 | 266
unlisted other sites
| recorded net completions |  |  |  | 431 | 517 | 493 | 358 | 336 | 270 | 256 | 247 | 303 | 372 | 343 | 230
net recorded completions
Total delivery
|  |  | plan year | year | 2016/17: tot comp; completions (sites over 5 net) 2017/18: small site
|  |  | 1 | 2005/6 | 2016/17: 233; completions (sites over 5 net) 2017/18: 116
|  |  | 2 | 2006/07 | 2016/17: 205; completions (sites over 5 net) 2017/18: 114
|  |  | 3 | 2007/08 | 2016/17: 405; completions (sites over 5 net) 2017/18: 167
|  |  | 4 | 2008/09 | 2016/17: 310; completions (sites over 5 net) 2017/18: 114
|  |  | 5 | 2010/11 | 2016/17: 228; completions (sites over 5 net) 2017/18: 43
|  |  | 6 | 2011/12 | 2016/17: 265; completions (sites over 5 net) 2017/18: 82
|  |  | 7 | 2012/13 | 2016/17: 230; completions (sites over 5 net) 2017/18: 86
|  |  | 8 | 2013/14 | 2016/17: 343; completions (sites over 5 net) 2017/18: 75
|  |  | 9 | 2014/15 | 2016/17: 372; completions (sites over 5 net) 2017/18: 86
|  |  | 10 | 2015/16 | 2016/17: 303; completions (sites over 5 net) 2017/18: 69
|  |  | 11 | 2016/17 | 2016/17: 247; completions (sites over 5 net) 2017/18: 82
|  |  | 12 | 2017/18 | 2016/17: 256; completions (sites over 5 net) 2017/18: 74
|  |  | 13 | 2018/19 | 2016/17: 270; completions (sites over 5 net) 2017/18: 99
|  |  | 14 | 2019/20 | 2016/17: 336; completions (sites over 5 net) 2017/18: 73
|  |  | 15 | 2020/21 | 2016/17: 358; completions (sites over 5 net) 2017/18: 60
|  |  | 16 | 2021/22 | 2016/17: 493; completions (sites over 5 net) 2017/18: 41
|  |  | 17 | 2022/23 | 2016/17: 517; completions (sites over 5 net) 2017/18: 29
|  |  | 18 | 2023/24 | 2016/17: 431; completions (sites over 5 net) 2017/18: 49
|  |  | 19 | 2024/25 | 2016/17: 0; completions (sites over 5 net) 2017/18: 0
|  |  | 20 | 2025/26 | 2016/17: 0; completions (sites over 5 net) 2017/18: 0
|  |  | Total delivery |  | 2016/17: 5802; completions (sites over 5 net) 2017/18: 1459
|  |  | average |  | 2016/17: 322.3333; completions (sites over 5 net) 2017/18: 81.0556